## Product Backlog
Product Backlog
User Story ID | User Story | Priority | Status | Sprint | Assigned to | Estimated effort (In days)
1 | Conduct site surveys and project evaluation. | High | In Progress | 1 | Project Manager | 1
2 | Develop architectural designs and blueprints. | High | In Progress | 1 | Architect | 5
3 | Obtain necessary permits and approvals. | High | Approved | 1 | Contractor | 2
4 | Lay foundations and construct basic infrastructure such as roads and utilities | Medium | In Progress | 1 | Civil Engineer | 5
5 | Monitor progress and quality. | Medium | Done | 1 | Project Manager | 5
6 | Estimate the cost and purchase construction materials. | High | In Progress | 2 | Supplier | 30
7 | Set up temporary site storage facilities. | Medium | Overdue | 2 | Civil Engineer | 20
8 | Clear and level the site. | High | In Progress | 3 | Contractor | 10
9 | Start digging for building foundations. | High | In Progress | 3 | Civil Engineer | 15
10 | Install basic utilities such as water supply, sewage, electricity. | Medium | On Hold | 3 | Contractor | 8
11 | Pour concrete and suitable materials to create a stable base for the houses. | Medium | In Progress | 4 | Contractor | 15
12 | Construct the frame of the houses like walls and roof. | High | In Progress | 4 | Civil Engineer | 30
13 | Install electrical systems. | High | On Hold | 4 | Electrician | 8
14 | Ensure proper drainage and sewage systems. | Medium | In Progress | 5 | Plumber | 5
15 | Install insulation and drywall. | Medium | In Progress | 5 | Interior Designer | 10
16 | Complete flooring and ceiling works. | Medium | In Progress | 5 | Interior Designer | 10
17 | Paint and finish walls. | High | In Progress | 6 | Painter | 5
18 | Create a design and sliding in the exterior. | High | Done | 6 | Exterior Designer | 5
19 | Install windows and doors. | High | In Progress | 6 | Exterior Designer | 6
20 | Set up outdoor lighting. | High | In Progress | 7 | Exterior Designer | 5
21 | Construct parking areas. | Medium | In Progress | 7 | Civil Engineer | 5
22 | Landscape gardens and green spaces. | Medium | Done | 7 | Landscaper | 5
23 | Install fencing and gates. | High | In Progress | 8 | Contractor | 2
24 | Conduct thorough inspections at each stage. | High | Needs Review | 8 | Surveyor | 2
25 | Check any issues or defects identified. | Medium | Needs Review | 8 | Surveyor | 2

## Estimated Budget
Estimated Budget
Features | Per unit Area in sqft | Rate per sqft | Cost per unit | For 5 units
Construction Cost | 1000 | 2500 | 2500000 | 12500000
Architectural And Design Fees
10% of Construction Cost |  |  | 250000 | 1250000
Contingency Cost
15% of Construction Cost |  |  | 375000 | 1875000
Total Estimated Budget |  |  | 3125000 | 15625000

## Sprint 1
Sprint 1
Project name | Row House Development | Start Date | Finish date | Overall Progress |  |  | Total Story Points | Total Duration
Project manager | Dipali Mendhe | 2025-03-03 | 2025-03-20 | 80% |  |  | 18 | 20
Task ID | Sprint Task | Feature type | Responsible Person | Story Points | Start Date | Finish Date | Duration | Status | % Completed
1 | Conduct site surveys and project evaluation. | Surveys | Project Manager | 1 | 2025-03-03 | 2025-03-05 | 2 | Done | 100%
2 | Develop architectural designs and blueprints. | Design | Architect | 5 | 2025-03-04 | 2025-03-09 | 5 | Done | 100%
3 | Obtain necessary permits and approvals. | Approvals | Contractor | 2 | 2025-03-08 | 2025-03-10 | 2 | In Progress | 70%
4 | Lay foundations and construct basic infrastructure such as roads and utilities | Construction | Civil Engineer | 5 | 2025-03-09 | 2025-03-15 | 6 | In Progress | 70%
5 | Monitor progress and quality. | Testing | Project Manager | 5 | 2025-03-15 | 2025-03-20 | 5 | Needs Review | 60%

## Sprint 2
Sprint 2
Project name | Row House Development | Start Date | Finish date | Overall Progress |  |  | Total Story Points | Total Duration
Project manager | Dipali Mendhe | 2025-03-03 | 2025-04-08 | 67.5% |  |  | 21 | 19
Task ID | Sprint Task | Feature type | Responsible Person | Story Points | Start Date | Finish Date | Duration | Status | % Completed
4 | Lay foundations and construct basic infrastructure such as roads and utilities | Construction | Civil Engineer | 3 | 2025-03-17 | 2025-03-20 | 3 | In Progress | 70%
6 | Estimate the cost and purchase construction materials. | Purchase | Supplier | 5 | 2025-03-17 | 2025-03-23 | 6 | In Progress | 70%
7 | Monitor progress and quality. | Testing | Project Manager | 5 | 2025-03-20 | 2025-03-22 | 2 | Needs Review | 60%
8 | Set up temporary site storage facilities. | Construction | Civil Engineer | 8 | 2025-03-28 | 2025-04-05 | 8 | In Progress | 70%
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Sprint 3
Sprint Plan 3
Project name | Row House Development | Start Date | Finish date | Overall Progress |  |  | Total Story Points | Total Duration
Project manager | Dipali Mendhe | 2025-03-03 | 2025-04-20 | 55% |  |  | 21 | 28
Task ID | Sprint Task | Feature type | Responsible Person | Story Points | Start Date | Finish Date | Duration | Status | % Completed
9 | Clear and level the site. | Construction | Contractor | 5 | 2025-03-31 | 2025-04-05 | 5 | In Progress | 70%
10 | Start digging for building foundations. | Construction | Civil Engineer | 3 | 2025-04-07 | 2025-04-11 | 4 | Not Started | 10%
8 | Set up temporary site storage facilities. | Construction | Civil Engineer | 5 | 2025-03-28 | 2025-04-08 | 11 | In Progress | 70%
11 | Install basic utilities such as water supply, sewage, electricity. | Installation | Contractor | 8 | 2025-04-12 | 2025-04-20 | 8 | In Progress | 70%
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Sprint 4
Sprint 4
Project name | Row House Development | Start Date | Finish date | Overall Progress |  |  | Total Story Points | Total Duration
Project manager | Dipali Mendhe | 2025-03-03 | 2025-05-01 | 77.5% |  |  | 24 | 26
Task ID | Sprint Task | Feature type | Responsible Person | Story Points | Start Date | Finish Date | Duration | Status | % Completed
12 | Pour concrete and suitable materials to create a stable base for the houses. | Construction | Contractor | 5 | 2025-04-14 | 2025-04-20 | 6 | Done | 100%
11 | Install basic utilities such as water supply, sewage, electricity. | Installation | Contractor | 8 | 2025-04-15 | 2025-04-21 | 6 | In Progress | 70%
13 | Construct the frame of the houses like walls and roof. | Construction | Civil Engineer | 8 | 2025-04-22 | 2025-05-03 | 11 | Overdue | 80%
14 | Install electrical systems. | Installation | Electrician | 3 | 2025-04-28 | 2025-05-01 | 3 | Needs Review | 60%
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Sprint 5
Sprint 5
Project name | Row House Development | Start Date | Finish date | Overall Progress |  |  | Total Story Points | Total Duration
Project manager | Dipali Mendhe | 2025-03-03 | 2025-11-03 | 50% |  |  | 18 | 22
Task ID | Sprint Task | Feature type | Responsible Person | Story Points | Start Date | Finish Date | Duration | Status | % Completed
15 | Ensure proper drainage and sewage systems. | Construction | Plumber | 5 | 2025-04-29 | 2025-05-04 | 5 | Not Started | 10%
16 | Install insulation and drywall. | Installation | Interior Designer | 5 | 2025-05-05 | 2025-05-12 | 7 | In Progress | 70%
17 | Complete flooring and ceiling works. | Interior | Interior Designer | 8 | 2025-05-13 | 2025-05-23 | 10 | In Progress | 70%

## Sprint 6
Sprint 6
Project name | Row House Development | Start Date | Finish date | Overall Progress |  |  | Total Story Points | Total Duration
Project manager | Dipali Mendhe | 2025-03-03 | 2025-06-03 | 60% |  |  | 13 | 14
Task ID | Sprint Task | Feature type | Responsible Person | Story Points | Start Date | Finish Date | Duration | Status | % Completed
18 | Paint and finish walls. | Painting | Painter | 3 | 2025-05-14 | 2025-05-17 | 3 | Needs Review | 60%
19 | Create a design and sliding in the exterior. | Design | Exterior Designer | 5 | 2025-05-17 | 2025-05-22 | 5 | In Progress | 70%
20 | Install windows and doors. | Installation | Exterior Designer | 5 | 2025-05-28 | 2025-06-03 | 6 | On Hold | 50%

## Sprint 7
Sprint 7
Project name | Row House Development | Start Date | Finish date | Overall Progress |  |  | Total Story Points | Total Duration
Project manager | Dipali Mendhe | 2025-03-03 | 2025-11-03 | 50% |  |  | 8 | 9
Task ID | Sprint Task | Feature type | Responsible Person | Story Points | Start Date | Finish Date | Duration | Status | % Completed
21 | Set up outdoor lighting. | Installation | Exterior Designer | 3 | 2025-05-28 | 2025-06-01 | 4 | Needs Review | 60%
22 | Construct parking areas. | Construction | Civil Engineer | 2 | 2025-06-03 | 2025-06-05 | 2 | Not Started | 10%
23 | Landscape gardens and green spaces. | Exterior | Landscaper | 3 | 2025-06-11 | 2025-06-14 | 3 | Overdue | 80%

## Sprint 8
Sprint 8
Project name | Row House Development | Start Date | Finish date | Overall Progress |  |  | Total Story Points | Total Duration
Project manager | Dipali Mendhe | 2025-03-03 | 2025-11-03 | 50% |  |  | 7 | 6
Task ID | Sprint Task | Feature type | Responsible Person | Story Points | Start Date | Finish Date | Duration | Status | % Completed
24 | Install fencing and gates. | Installation | Contractor | 2 | 2025-06-11 | 2025-06-13 | 2 | In Progress | 70%
25 | Conduct thorough inspections at each stage. | Surveys | Business Analyst | 2 | 2025-06-15 | 2025-06-17 | 2 | Not Started | 10%
26 | Monitor any issues or defects identified. | Testing | Business Analyst | 3 | 2025-06-25 | 2025-06-28 | 2 | In Progress | 70%
| Row Labels | Sum of Duration | Sum of % Completed
| 2025-06-11 | 2 | 70%
| Installation | 2 | 70%
| 2025-06-15 | 2 | 10%
| Surveys | 2 | 10%
| 2025-06-25 | 2 | 70%
| Testing | 2 | 70%
| Grand Total | 6 | 150%

## C.sprint
Cummulative Sprint
Project name | Row House Development | Start Date | Finish date | Overall Progress |  | Total Story Points | Total Duration
Project manager | Dipali Mendhe | 2025-03-03 | 2025-06-28 | 63.1% |  | 130 | 144
Task ID | Sprint Task | Feature type | Responsible Person | Story Points | Start Date | Finish Date | Duration | Status | % Completed
1 | Conduct site surveys and project evaluation. | Surveys | Project Manager | 1 | 2025-03-03 | 2025-03-05 | 2 | Done | 100%
2 | Develop architectural designs and blueprints. | Design | Architect | 5 | 2025-03-04 | 2025-03-09 | 5 | Done | 100%
3 | Obtain necessary permits and approvals. | Approvals | Contractor | 2 | 2025-03-08 | 2025-03-10 | 2 | In Progress | 70%
4 | Lay foundations and construct basic infrastructure such as roads and utilities | Construction | Civil Engineer | 5 | 2025-03-09 | 2025-03-15 | 6 | In Progress | 70%
5 | Monitor progress and quality. | Testing | Project Manager | 5 | 2025-03-15 | 2025-03-20 | 5 | Needs Review | 60%
4 | Lay foundations and construct basic infrastructure such as roads and utilities | Construction | Civil Engineer | 3 | 2025-03-17 | 2025-03-20 | 3 | In Progress | 70%
6 | Estimate the cost and purchase construction materials. | Purchase | Supplier | 5 | 2025-03-17 | 2025-03-23 | 6 | In Progress | 70%
7 | Monitor progress and quality. | Testing | Project Manager | 5 | 2025-03-20 | 2025-03-22 | 2 | Needs Review | 60%
8 | Set up temporary site storage facilities. | Construction | Civil Engineer | 8 | 2025-03-28 | 2025-04-05 | 8 | In Progress | 70%
9 | Clear and level the site. | Construction | Contractor | 5 | 2025-03-31 | 2025-04-05 | 5 | In Progress | 70%
10 | Start digging for building foundations. | Construction | Civil Engineer | 3 | 2025-04-07 | 2025-04-11 | 4 | Not Started | 10%
8 | Set up temporary site storage facilities. | Construction | Civil Engineer | 5 | 2025-03-28 | 2025-04-08 | 11 | In Progress | 70%
11 | Install basic utilities such as water supply, sewage, electricity. | Installation | Contractor | 8 | 2025-04-12 | 2025-04-20 | 8 | In Progress | 70%
12 | Pour concrete and suitable materials to create a stable base for the houses. | Construction | Contractor | 5 | 2025-04-14 | 2025-04-20 | 6 | Done | 100%
11 | Install basic utilities such as water supply, sewage, electricity. | Installation | Contractor | 8 | 2025-04-15 | 2025-04-21 | 6 | In Progress | 70%
13 | Construct the frame of the houses like walls and roof. | Construction | Civil Engineer | 8 | 2025-04-22 | 2025-05-03 | 11 | Overdue | 80%
14 | Install electrical systems. | Installation | Electrician | 3 | 2025-04-28 | 2025-05-01 | 3 | Needs Review | 60%
15 | Ensure proper drainage and sewage systems. | Construction | Plumber | 5 | 2025-04-29 | 2025-05-04 | 5 | Not Started | 10%
16 | Install insulation and drywall. | Installation | Interior Designer | 5 | 2025-05-05 | 2025-05-12 | 7 | In Progress | 70%
17 | Complete flooring and ceiling works. | Interior | Interior Designer | 8 | 2025-05-13 | 2025-05-23 | 10 | In Progress | 70%
18 | Paint and finish walls. | Painting | Painter | 3 | 2025-05-14 | 2025-05-17 | 3 | Needs Review | 60%
19 | Create a design and sliding in the exterior. | Design | Exterior Designer | 5 | 2025-05-17 | 2025-05-22 | 5 | In Progress | 70%
20 | Install windows and doors. | Installation | Exterior Designer | 5 | 2025-05-28 | 2025-06-03 | 6 | On Hold | 50%
21 | Set up outdoor lighting. | Installation | Exterior Designer | 3 | 2025-05-28 | 2025-06-01 | 4 | Needs Review | 60%
22 | Construct parking areas. | Construction | Civil Engineer | 2 | 2025-06-03 | 2025-06-05 | 2 | Not Started | 10%
23 | Landscape gardens and green spaces. | Exterior | Landscaper | 3 | 2025-06-11 | 2025-06-14 | 3 | Overdue | 80%
24 | Install fencing and gates. | Installation | Contractor | 2 | 2025-06-11 | 2025-06-13 | 2 | In Progress | 70%
25 | Conduct thorough inspections at each stage. | Surveys | Business Analyst | 2 | 2025-06-15 | 2025-06-17 | 2 | Not Started | 10%
26 | Monitor any issues or defects identified. | Testing | Business Analyst | 3 | 2025-06-25 | 2025-06-28 | 2 | In Progress | 70%
|  |  |  | Row Labels | Sum of Story Points | Sum of Duration |  | Sprint name | Story points | Duration
|  |  |  | Architect | 5 | 5 |  | Sprint 1 | 18 | 20
|  |  |  | Business Analyst | 5 | 4 |  | Sprint 2 | 21 | 19
|  |  |  | Civil Engineer | 34 | 45 |  | Sprint 3 | 21 | 28
|  |  |  | Contractor | 30 | 29 |  | Sprint 4 | 24 | 26
|  |  |  | Electrician | 3 | 3 |  | Sprint 5 | 18 | 22
|  |  |  | Exterior Designer | 13 | 15 |  | Sprint 6 | 13 | 14
|  |  |  | Interior Designer | 13 | 17 |  | Sprint 7 | 8 | 9
|  |  |  | Landscaper | 3 | 3 |  | Sprint 8 | 7 | 6
|  |  |  | Painter | 3 | 3 |  | Total | 130 | 144
|  |  |  | Plumber | 5 | 5
|  |  |  | Project Manager | 11 | 9
|  |  |  | Supplier | 5 | 6
|  |  |  | Grand Total | 130 | 144

## Dropdown_keys
Status |  | Priority | Feature Type | Responsible Person
Not Started | 0% | Low | Purchase | Project Manager
In Progress | 20% | Medium | Construction | Architect
Done | 100% | High | Design | Contractor
Overdue | 80% |  | Testing | Civil Engineer
Needs Review | 90% |  | Surveys | Supplier
Approved | 10% |  | Approvals | Electrician
On Hold | 50% |  | Installation | Plumber
|  |  | Interior | Interior Designer
|  |  | Painting | Exterior Designer
|  |  | Plumbing | Landscaper
|  |  | Exterior | Painter
|  |  | Hiring | Business Analyst